Drumsurn Village Plan

June 2018

CONTENTS

- BACKGROUND AND INTRODUCTION

- Why have a Village Plan

- About the Plan

- The Process

- Village Planning Framework

- THE BIG PICTURE

- Regional Policies and Plans

- Causeway Coast and Glens Borough Council Context

- THE LOCAL PICTURE

- Location, Context and History

- Socio- Economic Analysis

- Building on Foundations - Progress from work within Drumsurn

- WHAT PEOPLE SAID

- Consultation Process

- Summary Findings

- SWOT Analysis

- A VISION AND PLAN FOR DRUMSURN

- WHAT HAPPENS NEXT

Appendices

- Appendix 1 - Detailed Socio-Economic Profile

1.	BACKGROUND AND INTRODUCTION

Why Have a Village Action Plan?

Village Action Plans are being developed as part of the Northern Ireland Rural Development Programme Village Renewal measure operated by the Department of Agriculture, Environment and Rural Affairs.  This measure aims to ensure an integrated approach to assist villages and their surrounding areas to realise the potential of their economic, social, cultural and environmental resources.

This plan, for Drumsurn, was commissioned by Causeway Coast and Glens Borough Council with funding from the Council and DAERA.

About the Plan

This plan has evolved by consulting with local groups and residents to ensure that everyone could have a say and that actions put forward were those considered important to the majority and have the ability to implement.  The plan highlights actions that can be taken forward by people within the community; it can be used to influence statutory bodies and service providers and can be used as evidence of the need for various projects when applying for funding. The plan is designed to act as a framework for action in Drumsurn; it provides groups with a vision and direction for moving forward and shows collective will in developing the village for the benefits of locals and visitors alike.

The Process

The plan was developed over a number of months and involved local residents and groups in Drumsurn putting forward their views about how they would like to see their area develop over the next five years. Key to this process was revisiting the existing Village Plan to establish progress to date and identify those issues and actions which remain relevant, in addition to referencing for action any emerging concerns or projects ideas.

Village Planning Framework

Phase 1- Review and Analysis

- To carry out a detailed socio-economic analysis of the area to include population, age structure, health, education and economic activity.

- To consider the wider context, plans and policies that impact on the village, including Community Planning.

- To review any existing village plan and identify progress updates.

Phase 2- Research and key ideas

- To consult with key members of the community to make connections and understand how the village works.

- To carry out consultation meetings with local groups and organisations to enhance the new Village Plan and to ensure ideas are gathered.

- To analysis these ideas and separate them into groups and priorities.

Phase 3- Village Design and Development

- To highlight key ideas and look at ways to implement these putting in place a robust and realistic integrated village action plan identifying what needs to be done, why it is an issue, how it will be tackled, who will be involved and when it should happen

- Validate Plan with those involved.

2.	THE BIG PICTURE

Credit: Causeway Coast and Glens Community Plan

Community Plan

“The purpose of community planning is to develop a long term vision and plan for the Causeway Coast and Glens area and all its citizens based on thorough analysis of needs, priorities and opportunities in order to address them”. The Community Planning model establishes a clear focus on partnership and collaboration, working with local communities being a primary goal.

Acting as an integrated framework for development and delivery the Community Plan is a key strategic document for communities and villages across the Borough; as such each Village Plan will seek to contribute to the long term strategic outcomes set out in the Community Plan, namely:-

- A thriving economy

- A healthy safe community

- A sustainable accessible environment

A Thriving Economy

The Community Plan acknowledges the need for improved local employment opportunities, accessible skills training and learning, regeneration, modern infrastructure and the potential for innovation, including the use of the Borough’s unique natural assets. The village plan seeks to contribute to economic development in rural areas by identifying opportunities for growth and sustainability, including the social economy.

A Healthy Safe Community

This outcome area recognises that the Borough is predominantly rural and that this, along with projected ageing population growth, presents particular challenges in relation to both access to services and the threat of rural isolation, particularly amongst for older rural dwellers.  In addition to being concerned with the physical fabric and infrastructure of each village, the plans will also seek to address these challenges, recognising that overcoming them is integral to building cohesive and sustainable rural communities.

A Sustainable Accessible Environment

The Community Plan recognises the need to strive for balance in protecting and sustaining the Borough’s unique environment whilst also meeting community, tourism and commercial needs. This includes the need to provide fit for purpose infrastructure and access to services, including ease of access to outdoor spaces and the coastline for the benefit resident communities and visitors. Village plans reflect this at the local level, identifying actions which protect and respect the character of our rural communities while also supporting their growth and sustainability.

Northern Area Plan 2016

The Northern Area Plan 2016 is the development plan for the four legacy Council Areas of Ballymoney, Coleraine, Limavady and Moyle and operates as the local development plan for the Council area until the Council adopts its own Local Development Plan.

The Plan states that, in respect of Drumsurn, “Drumsurn has a significant residential function with good educational, social and recreational facilities. These include the high quality recreation grounds and community centre at St Matthew’s GAC to the south of the village”.

Local Development Plan

Local Development Plans form the basis of land use planning and decisions on planning applications within the Borough. They set out what the Council area will look like and how land should be used and developed. At the time of producing Village Plans (2017), Council’s Development Plan Team were in the initial stages of producing the Borough’s Local Development Plan 2030. A series of topic-based Discussion Papers had been drawn up to inform the process. Of relevance to the Village Plan for Drumsurn was the following:-

Education, Health, Community Facilities

- The village has a community centre owned and managed by Drumsurn Community Association

- The village is also served by a post office, pre-school, primary school and the community centre mentioned above (community owned, council supported)

Environment

- Drumsurn is recognised as an Area of Archaeological Potential and Area of Significant Archaeological Interest

- Site of Local Conservation Importance (SLNCI)

Transportation

- Northern Area Plan has identified a disused rail track bed: Limavady to Dungiven via Drumsurn

3.	THE LOCAL PICTURE

Location, Context and History

Drumsurn, set within the Roe Valley, is located 8 kilometres south east of Limavady and 10 kilometres north east of Dungiven. Drumsurn has a significant residential function with good educational, social and recreational facilities. These include the high quality recreation grounds and community centre at St Matthew’s GAC to the south of the village. However, Drumsurn provides only a limited range of commercial services. The village had a population of 357 in 2001. Drumsurn is designated a Village in the Settlement Hierarchy in Volume 1 of the Northern Area Plan.

Drumsurn Assets St Matthew’s GAC club Community Centre Council pitches at the Community Centre St Peter’s Hall Outdoor gym adjacent to the playing fields Primary and play school St Matthew’s Church Balteagh St Canice Church of Ireland

Socio- Economic Analysis

This is a new Village Plan for Drumsurn and uses statistics from the 2011 Census which became available from June 2013, along with the 2016 NISRA Mid-term Population Estimates and NI Multiple Deprivation Measure (NIMDM) 2010. The NIMDM 2010 has not been updated as yet, so figures from it remain unchanged. Drumsurn is located within the Forest Ward.

Drumsurn/Forest Ward

- The resident population of Forest Ward recorded at the 2011 Census was 2,432 people compared to 2,482 people at 30 June 2016 population estimates

- The population of increased by 1.33% between the 2001 and 2011 Census

- 21.48% (2011) of the resident population are under 16 years of age in comparison to the NI average of 20.8% (2016)

- 12.13% (2011) of the resident population are over 65 years of age in comparison to the NI average of 16% (2016)

- 52.47% of the usual resident population belong to or were brought up in the Catholic religion with 49.57% (2011) belong to or were brought up in the Protestant and other Christian Community background

- The percentage of local people with low or no qualifications was 46.28% in 2011, which is higher than the NI average of 23.65%

- 64.61% (2011) of adults between 16 – 74 years are economically active. This is lower than the NI average of 66.22% (2011)

- 18.99% (2011) of the population have a limiting long-term illness, health problems or disability

- Forest ward is one of the least deprived areas in NI, ranking within the top 52% (No change – NIMDM 2010 Index)

- Proximity to Services Deprivation ranks within the top 25% most deprived areas in NI (No change – NIMDM 2010 Index)

Building on Foundations

A number of significant developments and initiatives have been taken forward in and around Drumsurn village in recent years. Included in these are:-

- Drumsurn Community Association run the Baby and Toddler Group, Youth Club, Over 50s Group, craft classes, educational classes and seasonal activities

- Little Rascals Playgroup/Pre-school acquired a new building next to the primary school on 9th June 2017

- St Matthew’s GAC purchased land for a second pitch and secured planning permission for a new pitch. Fundraising is ongoing

- St Matthew’s GAC has been successful getting part funded to upgrade the club’s kitchen and toilet facilities

- St Matthew’s GAC have added the following facilities: one pitch for regulated games for ages 5 and upwards, one pitch for training for ages 5 and upwards, a gym is opened for anyone over the age of 16 (due to insurance reasons gym users have to become members of St Matthew’s GAC). The hall is available for various different activities, such as training in winter, dance classes etc.

- St Matthew’s GAC bring in different groups to talk to the community’s young people about depression, suicide and good mental health and wellbeing. The Club also books the Big Bus to give free health checks to its members

These developments provide a sound base for taking forward plans at both individual group and the wider village level. Drumsurn Community Association provides a valuable community presence, working at local level. A range of activity programmes and events are delivered from the community centre, which is owned and managed by Drumsurn Community Association.

Future initiatives and projects under consideration include:

- More community events throughout the year – create a calendar of community events

- Access more funding to provide educational and skills classes

- Extension of the Community Centre to replace the prefab currently used – this would provide a more energy efficient space with kitchen facilities

- Pathway between Little Rascals and the Primary School

- The extra room in the new Little Rascals building can be used for coffee mornings or classes

- Baby and toddler group: Outdoor space for outdoor play with shelter and storage space for play equipment

- Whilst the Community Association hosts a senior citizens’ dinner at Christmas, it would like to provide more for older people in the community

- Development of community allotments

- Provide adequate playpark provision to cater for all the children in the community

- Development of the pitches beside the Community Centre is being explored. Part of the field could be made into a great communal space. With good planning and reference to other models it has the potential to become a focal point for the village, it could offer an area not only for recreational purpose but for community events like Christmas fairs, outdoor market days, fundays and barbeques. Perhaps plant a Christmas tree on the site

- St Matthew’s GAC is continuing to ensure its facilities are of high quality and fit for use. It needs to invest in goalposts and the floor of the hall will need to be replaced. The Club is identifying sources of funding for these

4. WHAT PEOPLE SAID

Consultation Process

The Village Plan for Drumsurn was informed through:

- Consultation with local groups including:

  - Drumsurn Community Association

  - Baby and Toddler Group

  - Little Rascals Playgroup

  - St Matthew’s GAC

  - Gelvin Community Association

Consultation Feedback

In terms of the issues which the Drumsurn community identified as being in need of attention, these are summarised as follows:-

Environment and Infrastructure

Environmental improvements were suggested to improve the village appearance, for example allotments and a community garden and improve the green spaces generally. It was felt that re-locating the recycling bins from Little Rascals/Primary School area to a more central location (maybe beside the allotments) in the village would encourage more use of the bins. Another issue raised was the public right of way between the school and the chapel which needs a tarmac surface and the gates cleaned. Generally, there are potholes in the area that need repaired and grass verges and hedges need to be maintained to keep the village looking tidy, well-kept and welcoming.

Other suggested improvements include the construction of a nature pathway between Little Rascals and the Primary School for the whole community to use. Because of its location it will be visible from the road and so will add to improving the aesthetics of the village and make the village look more welcoming, it will link the pre-school and primary school and promote intergenerational activities.

Residents feel there is not much of a sense of arrival to the village, and the overall signage including directional signage to the community centre could be improved to promote the village, its facilities and assist visitors navigating Drumsurn.

Strong concerns were raised over road safety, in that the traffic drives too fast through the residential areas and the village overall, putting people and children in danger. Attempts at addressing excessive speed and increasing road safety awareness have been previously made and have worked to some extent, but it is felt that this is an ongoing problem and awareness of the issue needs to be heightened so that all drivers take responsibility for their speed.

The current community centre is a prefabricated building which was purchased ten years ago from the Education Authority. The majority of activities are centred around young people and include the Youth Club and the Baby and Toddler Group. It also provides classes throughout the year for adults when funding allows and activities for older people such as bingo, singing and Christmas dinners. It is a vital community asset which is in high and constant demand and options to secure its longevity are being examined. The community centre has secured funding to clad the outside of the building and fix its floor. Work is still required to address the lack of disabled toilet facilities, fix the walkway, tidy the outside area and improve the car park (currently it is hard core and is unsuitable for wheelchair users and buggies). In addition, the outdoor space at the community centre would be developed as it is not being used to its full potential; suggested uses are to enhance the learning and play experiences of children under 4 years.

Community Connections and Engagement

Groups contributing to the village planning exercise expressed a willingness to work together and participate in a shared vision for the village. In order to ensure that this enthusiasm is further progressed, support for capacity building will be required in order to support and progress the new village association which groups are keen to pursue.  In addition, the consultation highlighted that people recognised the importance of combining activities with all groups and better utilising existing facilities and promoting volunteering on an ongoing basis.

There is a strong volunteering culture in Drumsurn and for a lot of Drumsurn residents it begins with their joining the Youth Club as children. As they get older they are encouraged to become leaders and with support, guidance and example set by the adult volunteers they engage and participate in community life in Drumsurn through their volunteering efforts. This model has proven to work well for the village as Youth Club was started 30 years ago and Drumsurn Community Association shortly afterwards.

Health and Wellbeing

Discussions informing this theme included the importance of educational and skills classes, in which the community is brought together to participate in various short-term creative courses such as crochet or knitting. These types of classes were previously held and many people in Drumsurn enjoyed them and benefited from them as they felt more closely connected to their community and at the same time learnt new or improved existing skills. The classes came to an end due to lack of funding, but the community is very keen to see funding secured for new classes to be delivered.

The improved physical and mental health and wellbeing of Drumsurn’s older people was discussed during the consultations and it was agreed that more provision could be made for seniors in the community to reduce their isolation and loneliness and increase their social interaction. It was suggested this could be achieved through the provision of activities tailored to what older people enjoy such as coffee mornings, classes (hosted by Little Rascals as they have an extra room in their building that could be used for this) and encouraging intergenerational activities, for example the development of the nature pathway between Little Rascals and the Primary School for grandparents and their grandchildren to enjoy. The allotments and community gardens would also be of interest to some older people in Drumsurn.

5.	VISION AND PLAN FOR DRUMSURN

This Section puts forward the plan proposals for Drumsurn. An over-arching vision for the area is set out followed by proposals for action under each of the themes which emerged during the planning process.

Vision

The vision set out for Drumsurn is:

A well engaged rural village with good community spirit and quality of life where everyone works together to benefit the next generation

SWOT Analysis

Following analysis of community consultation feedback, a village SWOT analysis was developed for Drumsurn:

| Strengths | Weaknesses |
| --- | --- |
| - Small community where everyone comes together - Community spirit and enthusiastic people - Peaceful village lifestyle - Community facilities including the Community Centre, youth club, GAA club - Volunteering is encouraged and nurtured through the youth club - People are willing to volunteer to improve the community for everyone’s benefit and help with all aspects of community life - Sense of belonging - Mixed community coming together - The Community Centre involves all age groups | - Not enough for children and teenagers to do (with the exception of the youth club) - Road safety – speeding traffic through the village - Lack of directional signage for the Community Centre and other community facilities - Lack of adequate and suitable car parking at the Community Centre (currently hard core) and the surface is unsuitable for wheelchair users and buggies - Not enough play equipment in the park for children under 3 years old - Not enough street lighting between the post office and the shop, between the school and the chapel, and between the shop to the chapel - There are a lot of new people in the village and no opportunities to meet with them - Lack of allotments or community gardens - No sense of arrival to the village - No sense of festivity at Christmas |
| Opportunities | Threats |
| - Pitches at the Community Centre could be put to better use, e.g. allotments - Provide classes to learn new and develop existing skills, e.g. crochet, knitting, hairdressing, various group activities - Redevelopment of the large green area in the village e.g. allotments, community gardens or area for children to play - Development of/ update the play park as it is currently outdated and inadequate for the number of children who need it and for children under the age for 4 years old - Development of the facilities at the GAA club, e.g. floodlights, walking/running track | - Speeding traffic – residents feel that traffic calming is badly needed to keep their children safe - Lack of zebra/pedestrian crossing - The Community Centre requires renovation; it is the hub of the community and demand exceeds capacity. It caters for all age groups, it is becoming dated and requires attention for the “cradle to the grave” service it offers the whole community - Lack of funding for group activities and community events |

Findings from the consultation were drawn together under priority themes in order to take Drumsurn forward. As much as possible, the identified actions sought to build work done and currently being carried out by Drumsurn community groups and organisations, needs identified through consultation in addition to considering the wider policy and strategic environment, including the Community Plan for Causeway Coast and Glens. The following Action Plan was subsequently drawn up:-

Theme: Environment and Infrastructure

Rationale: To create an attractive, welcoming and accessible village environment, building on work already undertaken and maximising the village’s location

| Project Action | Why is it an Issue? | How Will it be Tackled? | Priority and Timeframe | Indicative Cost | Potential Funding Sources | Potential partners (inc. lead) | Linkages to Community Planning Outcomes |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Pathway between Little Rascals and Primary School | The space has the potential to be developed The pre-school and primary school will be linked Will improve the aesthetics of Drumsurn Everyone in the community will be welcome to use it Intergenerational activities will be promoted | Discuss ideas and plans with landscape architect Develop the pathway using gazebos and railway sleepers and keep it is natural as possible Source, apply for and secure funding | High – Year 1 | £40,000 | Council RDP | Little Rascals | Outcomes 1; 2; 4; 5; 6; 8; Health and Wellbeing; Children and young people have the best start in life; Safe; Positive relationships; Unique natural and built landscapes; Sustainably managed natural and built environment |
| Re-locate the recycling bins to a more central location in the village, perhaps beside the allotments | The bins are under used by the community Tidier and improved appearance of the village The community takes greater pride in the appearance of the village The community understands the importance of using bins and helping to protect the environment | Raise community awareness around the importance of protecting the environment and using the bins provided | High – Year 1 | Time investment to liaise with Council | - | All groups Council | Outcome 8; Sustainably managed natural and built environment |
| Allotments and a community garden and improve green spaces | Green spaces are underused An unused green space in the village would be given a new lease of life Contribute to the improved aesthetics of Drumsurn Contribute to improved health and wellbeing of the local community as they will be encouraged to get closer to nature Drumsurn will be more attractive to locals and visitors | Raise awareness amongst the community that green spaces are important assets in terms of conservation, environment, recreation and health and wellbeing | High – Year 1-2 | £20,000 | RDP Council | All groups | Outcomes 1; 2; 4; 5; 8; Health and Wellbeing; Children and young people have the best start in life; Safe; Positive relationships; Sustainably managed natural and built environment |
| Improve overall village signage including directional signage to the community centre | To assist visitors navigating the village Will direct visitors and tourists to village facilities Will help raise the profile of the community centre as an vital community asset | Liaise with the Council officers involved in directional signage | High – Year 1 - 2 | £10,000 | Council RDP | Council Drumsurn Community Association | Outcomes 6; 8; Unique natural and built landscapes; Sustainably managed natural and built environment |
| Explore feasibility of replacing existing prefab community centre: a more energy efficient space with kitchen facilities | The current prefab is in high demand and functioning at maximum capacity. At current usage rates it will not be fit for purpose in the near future. | Engage a consultant to assist the development of the feasibility study Carry out a feasibility study | High – Year 1 | £5,000 | Council RDP | Drumsurn Community Association | Outcome 7; Physical structures and facilitates that further growth, access and connections |
| Provision of additional facilities at the Community Centre | The current second hand prefab building is in high demand and functioning at maximum capacity. Funding has been secured from the council to clad the outside of the building and fix its floor. Work is still required to address the lack of disabled toilet facilities, fix the walkway, tidy the outside area and improve the car park (currently it is hard core and is unsuitable for wheelchair users and buggies). | Engage an architect and quantity surveyor to provide a conditions survey and quote Identify, apply for and secure funding | High – Year 1 | £30,000 | Council RDP | Drumsurn Community Association | Outcomes 8; Sustainably managed natural and built environment |
| Develop outdoor space at the Community Centre | Outside space is not being used to its full potential Enhance learning and play experiences of the children The outdoor space would be divided into specific areas for outdoor play with shelter and storage for play equipment and purpose built shelter to park buggies in | Agree a site plan, perhaps with the help of an architect Consider funding – source, apply for and secure funding Assign a project manager to oversee the development of the outdoor space | High – Year 1-2 | £100,000 | Council | Baby and Toddler Group | Outcomes 1; 2; 4; 5; 8; Health and Wellbeing; Children and young people have the best start in life; Safe; Positive relationships; Sustainably managed natural and built environment |
| Provision of additional equipment in the playpark | The current playpark is outdated and cannot accommodate the number of children who need it, nor is there any provision for children under 4 years old | Source, apply for and secure funding for adequate and appropriate playpark equipment | High – Year 1-2 | £30,000 | Council – to be aligned with the findings from Council’s play Audit | Drumsurn Community Association | Outcomes 1; 2; 4; Health and Wellbeing; Children and young people have the best start in life; Safe; |
| Between the school and the chapel there is a public right of way that needs a tarmac surface and the gates cleaned | Safety of the residents who use the right of way is compromised (This right of way is not adopted) Improve safety for users Improve aesthetics for locals and visitors | Lobby the council to arrange for the right of way to be adopted and tarmacked | Medium – Years 2 to 3 | £10,000 | Council | Council | Outcome 8; Sustainably managed natural and built environment |

Theme: Community Connections and Engagement

Rationale: Drumsurn benefits from strong community leadership and has a strong sense of community pride.  This is a strong base to build from in order to develop enhanced facilities, services and activities.

| Project Action | Why is it an Issue? | How Will it be Tackled? | Priority and Timeframe | Indicative Cost | Potential Funding Sources | Potential partners (inc. lead) | Linkages to Community Planning Outcomes |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Form a village forum bringing together all the voluntary groups in the village | Mobilise the community, and community organisations can link together to share resources Improve communication and build greater respect for each other’s efforts | Establish a village forum representative of all the local groups Sharing of plans and information Liaise with other villages to learn from their experiences | High – year 1 and ongoing | Time investment | - | Council All groups | Outcomes 5; 12; Positive relationships; Knowledgeable and skilled |
| Coffee mornings | Reduce isolation, loneliness and social exclusion Reduce social isolation and exclusion and greater community cohesion | Little Rascals have suggested the extra room in their building could be used by the community for coffee mornings | High and ongoing | - | - | Little Rascals | Outcomes 1; 4; 5; Health and Wellbeing; Safe; Positive relationships |
| Combine activities with all groups and better utilize existing facilities | Existing facilities can be better used, and groups can maximise available resources Efficient use of resources A better-connected community Greater community cohesion | Through the village forum share plans, ideas and information | High – Year 1 and ongoing | Time investment | - | All groups | Outcomes 1; 4; 5; Health and Wellbeing; Safe; Positive relationships |
| Promote volunteering | To ensure groups and projects have access to a pool of skilled volunteers to sustain their work Stronger sense of community People will develop new or existing skills and increase employability | Signage | High – Year 1 and ongoing | Time investment | - | All groups | Outcomes 5; 12; Positive relationships; Knowledgeable and skilled |
| Improve GAA hall to provide more community events | Need a multi-use facility for community events Events bring everyone together – projects of this kind would strengthen the community | Upgrade kitchen and toilets | High – Year 1 | £69,000 | Council | St Matthew’s GAC | Outcomes 5; 7 Positive relationships; Physical structures and facilities that further growth, access and connections |

Theme: Health and Wellbeing

Rationale: To ensure access to services and support is available for Drumsurn residents and visitors, contributing to community health and well-being

| Project Action | Why is it an Issue? | How Will it be Tackled? | Priority and Timeframe | Indicative Cost | Potential Funding Sources | Potential partners (inc. lead) | Linkages to Community Planning Outcomes |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Funding for educational and skills classes and community events, training and events for parents and children, classes for people (e.g knitting, crochet, baking, glass painting) | Reduce isolation, loneliness and empower the local community A more connected and empowered community Greater community cohesion More opportunities for people to get involved in hobbies and connect with their community through activities they enjoy Reduce social isolation and exclusion Improved mental health and wellbeing of local people Social interaction Regular active participation in activities people enjoy | Consult with the community to ascertain the types of classes and events they need and would like to see take place Develop and design programmes for delivery Identify appropriate funders Apply for and secure funding | High – year 1 and ongoing | £20,000 per annum | Big Lottery Council | All groups | Outcomes 1; 3; 5; 9; 12 Health and wellbeing; Access to services; Positive relationships; Contribute to and engage in a more prosperous and fair economy; Knowledge and skills |
| Provide more activities for the seniors in our community | Reduce isolation, loneliness and empower the local community Improved physical and mental health and wellbeing of local older people Social interaction Regular active participation in activities older people enjoy | Establish what the views, concerns, needs and aspirations of older people in Drumsurn are | High – Year 1 | - | - | All groups | Outcomes 1; 3; 5; Health and wellbeing; Live independently as far as possible access support services; Positive relationships |

Prioritisation:

In order to proceed with implementation, potential Village Renewal actions have been prioritised as follows:-

1.  Provision of additional facilities at the community centre –  refurbishment is necessary

2. Overall village signage including directional signage to the community centre

3. Develop a natural pathway between Little Rascals and the primary school which will be available for the whole community to use

4. Community allotments, community garden and improve green spaces

Community Planning Outcomes

Outcome 1:

All people of the Causeway Coast and Glens benefit from improved physical health and   mental wellbeing

Outcome 2:

Our children and young people will have the very best start in life

Outcome 3:

All people of the Causeway Coast and Glens can live independently as far as possible and access support services when they need it

Outcome 4:

The Causeway Coast and Glens area feels safe

Outcome 5:

The Causeway Coast and Glens area promotes and supports positive relationships

Outcome 6: The Causeway Coast and Glens area is widely recognised and celebrated for its unique natural built landscapes

Outcome 7: The Causeway Coast and Glens area has physical structures and facilities that further growth, access and connections

Outcome 8: The Causeway Coast and Glens has a sustainably managed natural and built

Environment

Outcome 9: The Causeway Coast and Glens area provides opportunities for all to contribute to and engage in a more prosperous and fair economy

Outcome 10: The Causeway Coast and Glens area attracts and grows more profitable businesses

Outcome 11: The Causeway Coast and Glens area drives entrepreneurship and fosters innovation

Outcome 12: All people of the Causeway Coast and Glens will be knowledgeable and skilled

Other Considerations

Every effort has been made to ensure that the action plans developed for each village are comprised of realistic and achievable project actions. In some cases, issues have been raised which are of real concern to local people but may be beyond the remit of the Village Plan – aspirational as opposed to achievable. In these instances, such issues are identified in the Village Plan as a concern but have not been included as a practical action point.

With respect to Drumsurn, the following issues have been raised:-

- Between the primary school and the chapel there is a public right of way that needs tarmacked

- Redevelopment of the community centre to include car parking

- Multi-use facility for community events

- The lights around the pitch at St Matthew’s GAC are not fit for purpose and need replaced

- Development of a MUGA pitch

6.	WHAT HAPPENS NEXT

It is recommended that Drumsurn Community Association establish a sub-committee to provide a co-ordination role to ensure the actions within this Plan are progressed.  The sub-committee should be representative of the village community and should involve public, private and community interests.

Individual project actions will be taken forward by relevant organisations, individuals or collectives as identified in the Action Plan. Only the people in the area, familiar with its history and offerings, can make the Action Plan become reality.

As groups research and investigate the best way forward in each project area, the full financial implications will become known and applications for funding and fund-raising activities will take place.  It is recognised that Council and RDP will not have sufficient funds to carry out all the activities in this plan and other sources of funding will be required.  The full Village Plan provides details of potential opportunities to grasp.

The Association will liaise with Causeway Coast and Glens Borough Council on an ongoing basis to monitor progress and implementation of identified actions.

Appendix 1 – Detailed Socio-Economic Profile

Drumsurn is located in the Forest Ward

Population estimates

The estimated population of Forest Ward at 30 June 2016 was 2,482, of which 1,262 (50.8%) were male and 1,220 (49.2%) were female.

This was made up of:

- 513 children aged 0-15 years

- 759 people aged 16-39 years

- 856 people aged 40-64 years

- 354 people aged 65 years and older

Between 2006 and 2016 the population of Forest Ward increased by 21 people or 0.9%.

Usually resident population

On Census Day 27 March 2011, the usually resident population of Forest Ward was 2,449 accounting for 0.14% of the NI total.

Households

On Census Day 27th March 2011, there were 2,449 people (100.00%) of the usually resident population) living in 859 households, giving an average household size of 2.85.

Demography

On Census Day 27th March 2011, in Forest Ward:

- 21.48% were aged under 16 years and 12.13% were aged 65 years and over

- 50.43% of the usually resident population were male and 49.57% were female

- 37 years was the average (median) age of the population

Ethnicity, identity, language and religion

On Census Day 27th March 2011, in Forest Ward, considering the resident population:

- 99.59% were from the white (including Irish traveller) ethnic group

- 52.47% belong to or were brought up in the Catholic religion and 44.59% belong to or were brought up in a ‘Protestant and Other Christian (including Christian related)’ religion

- 49.65% indicated that they had a British national identity, 26.26% had an Irish national identity and 30.75% had a Northern Irish national identity

*Respondents could indicate more than one national identity

On Census Day 27th March 2011, in Forest Ward, considering the population aged 3 years old and over:

- 7.94% had some knowledge of Irish

- 9.90% had some knowledge of Ulster Scots

- 0.21% did not have English as their first language

Health

On Census Day 27th March 2011, in Forest Ward:

- 18.99% of people had a long-term health problem or disability that limited their day-to-day activities

- 81.05% of people stated their general health was either good or very good

- 10.90% of people stated that they provided unpaid care to family, friends, neighbours or others

Housing and accommodation

On Census Day 27th March 2011, in Forest Ward:

- 79.98% of households were owner occupied and 16.41% were rented

- 37.14% of households were owned outright

- 6.29% of households were comprised of a single person aged 65+ years

- 6.98% were lone parent households with dependent children

- 8.85% of households did not have access to a car or van

Qualifications

On Census Day 27th March 2011, considering the population aged 16 years old and over:

- 17.32% had a degree or higher qualification

- 46.28% had no or low (Level 1*) qualifications

*level 1 is 1-4 O Levels/GCE/GCSE (any grades) or equivalent

Labour market

On Census Day 27th March 2011, considering the population aged 16 to 74 years old:

- 64.61% were economically active, 35.39% were economically inactive

- 56.62% were in paid employment

- 5.69% were unemployed

Deprivation

The Northern Ireland Multiple Deprivation Measure (NIMDM) 2010 provides information on seven types of deprivation and overall measure of multiple deprivation for small areas. NISRA has recently been commissioned to initiate work to update this Measure with a view to publish results mid-2017. See the NISRA website for further information on Deprivation.

Wards are ordered from most deprived to least deprived on each type of deprivation and then assigned a rank. The most deprived is ranked 1, and as there are 582 wards, the least deprived ward has a rank of 582. The deprivation rankings for Forest Ward are given in the table below.

|  | Rank Forest |
| --- | --- |
| Multiple Deprivation Measure | 300 |
| Income Deprivation | 350 |
| Employment Deprivation | 197 |
| Health Deprivation and Disability Deprivation | 360 |
| Education Skills and Training Disability | 267 |
| Proximity to Services Deprivation | 142 |
| Crime and Disorder | 402 |
| Living Environment | 558 |

A Better Future Together – A Community Plan for Causeway Coast and Glens 2017 - 2030

Northern Area Plan 2016 page 153