Macosquin Village Plan

June 2018

CONTENTS

- BACKGROUND AND INTRODUCTION

- Why have a Village Plan

- About the Plan

- The Process

- Village Planning Framework

- THE BIG PICTURE

- Regional Policies and Plans

- Causeway Coast and Glens Borough Council Context

- THE LOCAL PICTURE

- Location, Context and History

- Socio- Economic Analysis

- Building on Foundations - Progress from the Previous Village Plan

- WHAT PEOPLE SAID

- Consultation Process

- Summary Findings

- SWOT Analysis

- A VISION AND PLAN FOR MACOSQUIN

- WHAT HAPPENS NEXT

Appendices

- Appendix 1 - Detailed Socio-Economic Profile

1.	BACKGROUND AND INTRODUCTION

Why Have a Village Action Plan?

Village Action Plans are being developed as part of the Northern Ireland Rural Development Programme Village Renewal measure operated by the Department of Agriculture, Environment and Rural Affairs.  This measure aims to ensure an integrated approach to assist villages and their surrounding areas to realise the potential of their economic, social, cultural and environmental resources.

This plan, for Macosquin, was commissioned by Causeway Coast and Glens Borough Council with funding from the Council and DAERA.

About the Plan

This plan has evolved by consulting with local groups and residents to ensure that everyone could have a say and that actions put forward were those considered important to the majority and have the ability to implement.  The plan highlights actions that can be taken forward by people within the community; it can be used to influence statutory bodies and service providers and can be used as evidence of the need for various projects when applying for funding. The plan is designed to act as a framework for action in Macosquin; it provides groups with a vision and direction for moving forward and shows collective will in developing the village for the benefits of locals and visitors alike.

The Process

The plan was developed over a number of months and involved local residents and groups in Macosquin putting forward their views about how they would like to see their area develop over the next five years. Key to this process was revisiting the existing Village Plan to establish progress to date and identify those issues and actions which remain relevant, in addition to referencing for action any emerging concerns or projects ideas.

Village Planning Framework

Phase 1- Review and Analysis

- To carry out a detailed socio-economic analysis of the area to include population, age structure, health, education and economic activity.

- To consider the wider context, plans and policies that impact on the village, including Community Planning.

- To review any existing village plan and identify progress updates.

Phase 2- Research and key ideas

- To consult with key members of the community to make connections and understand how the village works.

- To carry out consultation meetings with local groups and organisations to enhance the new Village Plan and to ensure ideas are gathered.

- To analysis these ideas and separate them into groups and priorities.

Phase 3- Village Design and Development

- To highlight key ideas and look at ways to implement these putting in place a robust and realistic integrated village action plan identifying what needs to be done, why it is an issue, how it will be tackled, who will be involved and when it should happen

- Validate Plan with those involved.

2.	THE BIG PICTURE

Credit: Causeway Coast and Glens Community Plan

Community Plan

“The purpose of community planning is to develop a long term vision and plan for the Causeway Coast and Glens area and all its citizens based on thorough analysis of needs, priorities and opportunities in order to address them”. The Community Planning model establishes a clear focus on partnership and collaboration, working with local communities being a primary goal.

Acting as an integrated framework for development and delivery the Community Plan is a key strategic document for communities and villages across the Borough; as such each Village Plan will seek to contribute to the long term strategic outcomes set out in the Community Plan, namely:-

- A thriving economy

- A healthy safe community

- A sustainable accessible environment

A Thriving Economy

The Community Plan acknowledges the need for improved local employment opportunities, accessible skills training and learning, regeneration, modern infrastructure and the potential for innovation, including the use of the Borough’s unique natural assets. The village plan seeks to contribute to economic development in rural areas by identifying opportunities for growth and sustainability, including the social economy.

A Healthy Safe Community

This outcome area recognises that the Borough is predominantly rural and that this, along with projected ageing population growth, presents particular challenges in relation to both access to services and the threat of rural isolation, particularly amongst for older rural dwellers.  In addition to being concerned with the physical fabric and infrastructure of each village, the plans will also seek to address these challenges, recognising that overcoming them is integral to building cohesive and sustainable rural communities.

A Sustainable Accessible Environment

The Community Plan recognises the need to strive for balance in protecting and sustaining the Borough’s unique environment whilst also meeting community, tourism and commercial needs. This includes the need to provide fit for purpose infrastructure and access to services, including ease of access to outdoor spaces and the coastline for the benefit resident communities and visitors. Village plans reflect this at the local level, identifying actions which protect and respect the character of our rural communities while also supporting their growth and sustainability.

Northern Area Plan 2016

The Northern Area Plan 2016 is the development plan for the four legacy Council Areas of Ballymoney, Coleraine, Limavady and Moyle and operates as the local development plan for the Council area until the Council adopts its own Local Development Plan.

The Plan states that, in respect of Macosquin, “Macosquin has excellent road links with most of County Londonderry/Derry and Mid-Ulster. ”.

Local Development Plan

Local Development Plans form the basis of land use planning and decisions on planning applications within the Borough. They set out what the Council area will look like and how land should be used and developed. At the time of producing Village Plans (2017), Council’s Development Plan Team were in the initial stages of producing the Borough’s Local Development Plan 2030. A series of topic-based Discussion Papers had been drawn up to inform the process. Of relevance to the Village Plan for Macosquin was the following:-

Environment

- Macosquin is one of 20 settlements in the Borough with identified areas of Archaeological Potential Macosquin River, St Marys are included in the list of Local Landscape Policy Areas (LLPAs). LLPAs ensure that new development does not dominate areas of distinctive landscape and townscape character. LLPA designations protect features considered of value to the local landscape setting

Transportation

- There are walkways away from the local road network that provide local linkages to facilities and services. these pedestrian linkages provide safe and convenient routes between residential areas and the school, church, shop and post office, pub and allotments

Education, Health, Community Facilities

- Village is also served by a post office, library, one pre-school, one primary school

- Macosquin Primary School was one of ten in the Borough that was over-subscribed at June 2015

- Macosquin does not have a council recognised community hall or centre, but Macosquin does have the Church Hall and Community House, however both require investment

3.	THE LOCAL PICTURE

Location, Context and History

The origins of Macosquin go back to a 6thCentury monastic settlement. Features remain from its subsequent development as a Plantation village laid out at the beginning of the 17th Century. The village has a primary school, a general store and a modest range of social and recreational facilities.

Macosquin is located immediately west of Dunhill Road, part of the Northern Transport Corridor, 4 kilometres south of Coleraine. The A29 Drumcroone Road, a protected route and link corridor, joins with the A37 a short distance east of the village. Therefore, Macosquin has excellent road links with most of County Londonderry/Derry and Mid-Ulster. However, it is only served by a limited bus service.

Following rapid growth in the 1950s and 1960s, the village had a peak population of over 800 in the 1970s, but subsequently has declined to a 2001 population of 594. After an almost total absence of development in the 1990s, there has been an increase in private house building, strengthening the village’s residential function. Macosquin is designated a Village in the Settlement Hierarchy in the Northern Area Plan.

Macosquin Assets - Macosquin Community House - Lower Parish Centre - Macosquin Primary School - Preschool playgroup - Playpark - Green spaces throughout the village - Picnic area along main Coleraine to Derry/Londonderry Road - Church buildings - Football pitch

It is recognised that some of these assets are in good condition whilst others require additional work or investment to maintain their integrity/quality or to bring them back to an acceptable level of condition.

Socio-Economic Analysis

The previous Macosquin Village Plan (2011), used statistics from the 2001 Census and the NI Multiple Deprivation Measure (NIMDM) 2010. Figures from the 2011 Census became available from June 2013, and this report uses them along with mid-2016 NISRA Mid-term Population Estimates. The NIMDM 2010 has not been updated as yet, so figures from it remain unchanged. (Please note: Figures in italics are those from the previous Village Plan, to allow for comparison).

Macosquin

- The resident population of Macosquin recorded at the 2011 Census was 614 people (596 persons (2001))

- The population increased by 8.71% between the 2001 and 2011 Census

- 21.82% (2011) (21.8% 2001) of the resident population are under 16 years of age in comparison to the NI average of 20.8% (2016) (23.6% (2001))

- 13.68% (2011) (16.8% 2001) of the resident population are over 65 years of age in comparison to the NI average of 16% (2016) (13.25% (2001))

- 4.07% of the usual resident population belong to or were brought up in the Catholic religion (2.4% (2001)) with 91.86% (2011) (96.3% (2001)) belong to or were brought up in the Protestant and other Christian Community background

- Percentage of local people with low or no qualifications has fallen very slightly in 10 years from 57.8% in 2001 to 57.08% in 2011, but is still higher than the NI average of 23.65% (58.9% (2001)

- 62.56% (2011) of adults between 16 – 74 years are economically active.  This is lower than the NI average of 66.22% (2011)

- 18.08% (2011) (20% 2001) of the population have a limiting long-term illness, health problems or disability

- Macosquin is one of the least deprived areas in NI, ranking within the top 60-65% (No change – NIMDM 2010 Index)

- Proximity to Services ranks at 30% (No change – NIMDM 2010 Index)

Building on Foundations

Some developments and initiatives have been taken forward or sustained in and around Macosquin village in recent years. Included in these are:-

- Community House

- Macosquin Pre-School Group

These developments provide a sound base for taking forward plans at both individual group and the wider village level. Mascosquin Village Community Association provides a valuable community presence, working at local level. A range of activity programmes and events are delivered from the Community House, which is owned and managed by Macosquin Village Community Association.

Future initiatives and projects under consideration include:

- Looking into Escape Rooms Portsmouth for a trip with the teenagers and also looking to price buses for the trip

- A tidy up for the village with kids, possible a BBQ or food after the street clean up

- The windows and doors of Farranseer Park houses need replaced as they are in bad condition and most residents are complaining

- Cars parked on the road at the Upper Church Hall – people can’t get access to the footpath

- There are no street lights up to the Church hall which is very dangerous

- The back lane to the shop has a light but it has stopped working

4. WHAT PEOPLE SAID

Consultation Process

The Village Plan for Macosquin was informed through:

- Review of previous 2011 Village Plan

- Consultation with local groups including:

  - Macosquin Village Community Association

  - Macosquin Pre-School Group

  - St Mary’s Church

  - Macosquin FC

Consultation informing the Village Plan was undertaken through consultation with members of the above community organisations and a community drop in event.  On completion of initial consultations, a draft Action Plan was drawn up and circulated for discussion. This afforded the opportunity to review the proposed actions and confirm priority needs and issues. A final Village Plan and Action Plan was then produced.

Summary Findings

In terms of the issues which the Macosquin community identified as being in need of attention, these are summarised as follows:-

Encourage greater participation in the community

There is clear feedback from the existing community volunteers that it is difficult to encourage new volunteers into the community organisations in Macosquin.  Mascosquin Village Community Association generally takes a lead in both the management of the Community House and attempting to secure additional funds to deliver new activities or services. Some of the members feel that there is apathy within the community and others feel that they need a new injection of skills and experience in the Association in order to further its work.

Need for more and younger volunteers

This relates to the participation by the wider community; some of the volunteers involved at the moment are older and there is consensus that new energetic volunteers are required in order to re-energize the work of the Association.

Develop and sustain services for the community

It is recognized that Macosquin is a relatively small community. However, existing community facilities require upgrading in order to meet the needs of the community and to ensure that they are `fit for purpose` for the next ten years. The Macosquin Village Community Association has secured a long-term lease of the Community Houses from NIHE. This creates the opportunity for it to examine a longer-term Vision of developing these buildings as a Community Hub for Basic Services delivery and to better meet the needs of Macosquin Pre-School Group. There are access, inclusion, energy efficiency and storage issues associated with the current premises. The Church Hall and the Football pitch would also require investment to render them in line with acceptable standards for 2018. The MUGA and playpark are important community assets. There is a feeling within the community that more work needs to be done to ensure that health and safety issues are addressed (particularly at the playpark) and that the overall condition and presentation of both the MUGA and Playpark are enhanced. Car parking at the Primary School is a significant and important issue for the community. The vehicular access through a “back lane” is restricted and this conflicts with pedestrian users, particularly those with buggies.  There is a feeling within the community that this is a health and safety issues waiting to happen.

Promote local heritage and preserve the environment

A significant portion of the village is older and presents quality heritage which requires to be maintained and sustained. Directional signage in the village would help people to find key assets and community / public buildings. This should be matched with interpretive panels which help tell the story of Macosquin. The overall presentation of the village requires to be addressed (in part).  There is a clear feeling that NIHE must take a much more focused view of the maintenance of its housing stock and the surrounding sites i.e. laneways, access ways, cleaning of tarmacs and litter picking.

5.	VISION AND PLAN FOR MACOSQUIN

Introduction

This Section puts forward the plan proposals for Macosquin. An over-arching vision for the area is set out followed by proposals for action under each of the themes which emerged during the planning process.

Vision

The vision set out for Macosquin in the previous Village Plan and reinforced here is:-

A cleaner, tidier, well managed and welcoming village reflecting community pride and participation

SWOT Analysis

Following analysis of community consultation feedback, a village SWOT analysis was developed for Macosquin:

| Strengths | Weaknesses |
| --- | --- |
| - Well established Community Association - Site of Cistercian Abbey - Plantation Village - Good history of community engagement and achievement - Potential to develop walks in the immediate area - Active participants on Inter-agency housing forum - Well located close to main arterial routes to Derry/Londonderry and Coleraine - Active Macosquin Village Community Association - Strong pre-school provision | - Football pitch in need of drainage, and new turf - Poor signage at village entrance - Limited ideas for village promotion - Lack of public seating - Lack of up to date informative and interpretative signage - Village has no impact on passing motorist/visitor - Lack of up to date informative and interpretive signage - Lack of effective signage on A37 - The windows and doors of Farranseer Park houses need replaced as they are in bad condition and most residents are complaining - Cars parked on the road at the Upper Church Hall – people can’t get access to the footpath - There are no street lights up to the Church hall which is very dangerous - The back lane to the shop has a light but it has stopped working - Broadband very poor |
| Opportunities | Threats |
| - To enhance the existing Community House to increase space for basic service provision - RDP Village Renewal - To develop Community House as a Community Hub for delivery of Basic Services - Village Plan will help focus group efforts - To improve the image of the village - Possibility of village renewal funding - Ability to focus on a 5 year plan with short, medium and long term goals - To promote greater participation in village life by non-NIHE tenants - To record the history and story of Macosquin - To maximize support from politicians and agencies - To create a new and positive sense of civic pride in the village | - There is apathy in the village for joining the committee for the Village Association - Only one village shop - Not securing needed funds to deliver the plan - Tensions around murals and cultural expression |

Findings from the consultation were drawn together under priority themes in order to take Macosquin forward.  They are reflective of the previous Village Plan themes in order to provide consistency; in some cases themes have been amalgamated to provide greater cohesion and efficiency in implementation.

As much as possible, the identified actions sought to build on the previous plan in addition to needs identified through consultation in addition to considering the wider policy and strategic environment, including the Community Plan for Causeway Coast and Glens. The following Action Plan was subsequently drawn up:-

Theme: Encourage greater participation in the community

Rationale: Macosquin benefits from strong community leadership and has a strong sense of community pride.  This is a strong base to build from to develop enhanced facilities, services and activities.

| Project Action | Why is it an Issue? | How Will it be Tackled? | Priority and Timeframe | Indicative Cost | Potential Funding Sources | Potential partners (inc. lead) | Linkages to Community Planning Outcomes |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Promote Volunteering | There is a lack of new volunteers to support the Association and help deliver the Village Plan | Host a volunteer recruitment event and provide volunteer training | High: Year 1 | £1,000 | Council Small Grant Scheme | Community Association |  |

Theme: Develop and sustain services for the community

Rationale: To ensure access to services and support is available for Macosquin residents, contributing to opportunities for personal development, business growth and tourism

| Project Action | Why is it an Issue? | How Will it be Tackled? | Priority & Timeframe | Indicative Cost | Potential Funding Sources | Potential partners (inc. lead) | Linkages to Community Planning Outcomes |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Car parking |  |  |  |  |  |  |  |
| Play Area | The play area is poorly presented and is not designed to meet the needs of younger children; especially pre-school children (under 4) This will result in a safe and accessible playa re for under 11s and designed to meet the needs of pre-school children | 1. confirm the assessment of need in the Council’s forthcoming Play Strategy 2. Liaise with the Council’s capital team to agree a suitable design 3. Lobby via the local Councillor for the area to ensure that the play area is redeveloped in line with the Council’s Play Policy and schedule for investing in play facilities | High – Year 1 | £50,000 | Council as part of its ongoing programme of investing in play facilities across the Borough | Council | Outcomes 1; 2; 4; Health and Wellbeing; Children have the best start in life; Safe |
| Picnic Area | The picnic area adjacent to Macosquin is on a main arterial route into and out of Coleraine town. It is very poorly maintained and there is no particularly strong signage to identify it | 1. Develop a concept for a new area which incorporates a stop and picnic area and some interpretation of Macosquin 2. Cost and seek funding | Medium – Years 2 - 3 | £30,000 | RDP Village Renewal | Council | Outcomes 4; 8; Safe; Sustainably managed natural and built environment |
| Community House Access | Community House is an important building for the delivery of basic services in Macosquin. It is a two storey building (former NIHE house) and requires a lift to make the first floor accessible and to comply with DDA 1995. It would benefit from some additional space to facilitate an enhanced programme of services and activities | 1. Examine options to include a lift and improve available and useable space 2. Clarify impact from a planning perspective 3. Cost options 4. Procure a contractor to undertake the works | High -Years 1 – 2 | £100,000 | RDP Basic Services/ Council Capital programme | Community Association | Outcomes 1; 2; 3; 4; 5 Health and Wellbeing; Children and young people have the best start in life; People can live independently as far as possible and access support services; Safe; Positive relationships |
| Changing facilities and pitch are not fit for purpose | The current pitch is poorly drained, and the changing facilities are poor/ non-existent. There are no floodlights to support evening and out of summer activities or programmes | 1. Agree future of pitch and whether there is a willingness and support to develop additional facilities 2. Planning has been passed for floodlights to be installed | High – Years 1 - 2 | £50,000 for the football pitch £130,000 for the floodlights |  |  | Outcomes 1; 2; 4; 5 Health and Wellbeing; Children and young people have the best start in life; Safe; Positive relationships |
| Church Hall | The current Church Hall is dated, is cold and requires investment | - Carry out conditions survey - Consult with members and confirm need - Examine and cost options | Medium – Years 2 - 3 | £100k | HLF | HLF | Outcomes 4; 8; Safe; Sustainably managed natural and built environment |
| Car parking near the school | Health and safety issues occur between pedestrians and cars during mornings and evenings at school | 1. Identify car parking options 2. Secure land, planning and and capital | Medium – Years 3 – 5 | TBC | Education Authority | Education Authority | Outcomes 1; 2; 4 Health and Safety; Children and young people have the best start in life; Safe |

Theme: Promote local heritage and preserve the environment

Rationale: To create an attractive, welcoming and accessible village environment, building on work already undertaken and maximising the village’s coastal location

| Project Action | Why is it an Issue? | How Will it be Tackled? | Priority and Timeframe | Indicative Cost | Potential Funding Sources | Potential partners (inc. lead) | Linkages to Community Planning Outcomes |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Village Centre Appearance | The overall presentation of Macosquin is poor and there are a number of vacant premises The grass at the entrance of the village needs cutting This will result in a more attractive village for the local community and a better first impression for visitors to it | 1. develop an agreed approach to landscaping some areas in and around the village; the community members will identify potential locations 2. Examine shop front infill panels as an option | High – Year 1 | £40,000 | RDP Village Renewal | TBC | Outcome 8; Sustainably managed natural and built environment |
| Allotments | Significant work has been carried out working up an allotment project. There is still demand but the project has not proceeded as there is no available lease for the land. | 1. Identify suitable site 2. Develop concept and cost the scheme | High – Year 1 | £30,000 | RDP Village Renewal | TBC | Outcomes 1; 4; 5; 8; Health and Wellbeing; Safe; Positive relationships; Sustainably managed natural and built environment |
| Signage | There is poor signage on the main arterial route identifying Macosquin or providing directions for visitors when they enter the village | 1. Confirm a design option and locations 2. Assess planning implications 3. Agree costs and leadership of the project | High – Year 1 | £20,000 | RDP Village Renewal | TBC | Outcome 8; Sustainably managed natural and built environment |

Prioritisation:

In order to proceed with implementation, potential Village Renewal actions have been prioritised as follows:-

- Village signage scheme

- Compliance work to Community House

- Playing pitch additions

- Allotment scheme

Community Planning Outcomes

Outcome 1:

All people of the Causeway Coast and Glens benefit from improved physical health and   mental wellbeing

Outcome 2:

Our children and young people will have the very best start in life

Outcome 3:

All people of the Causeway Coast and Glens can live independently as far as possible and access support services when they need it

Outcome 4:

The Causeway Coast and Glens area feels safe

Outcome 5:

The Causeway Coast and Glens area promotes and supports positive relationships

Outcome 6: The Causeway Coast and Glens area is widely recognised and celebrated for its unique natural built landscapes

Outcome 7: The Causeway Coast and Glens area has physical structures and facilities that further growth, access and connections

Outcome 8: The Causeway Coast and Glens has a sustainably managed natural and built

Environment

Outcome 9: The Causeway Coast and Glens area provides opportunities for all to contribute to and engage in a more prosperous and fair economy

Outcome 10: The Causeway Coast and Glens area attracts and grows more profitable businesses

Outcome 11: The Causeway Coast and Glens area drives entrepreneurship and fosters innovation

Outcome 12: All people of the Causeway Coast and Glens will be knowledgeable and skilled

Other Considerations

Every effort has been made to ensure that the action plans developed for each village are comprised of realistic and achievable project actions. In some cases, issues have been raised which are of real concern to local people but may be beyond the remit of the Village Plan – aspirational as opposed to achievable. In these instances, such issues are identified in the Village Plan as a concern but have not been included as a practical action point.

With respect to Macosquin, the following issues have been raised:-

- The need for NIHE to place emphasis on the maintenance and upkeep of properties

- The requirement for a more regular mowing of grass and clearing of paths

- There are willing community volunteers and organisations; they need support to lobby and to effectively engage in challenge funding processes

6.	WHAT HAPPENS NEXT

It is recommended that a Village Action Plan Steering Committee be formed.  This Steering Committee will form a coordination role to ensure the actions within this Plan are progressed. The Steering Committee should be representative of the village community and should involve public, private and community interests.

Individual project actions will be taken forward by relevant lead organisations, individuals or collectives as identified in the Action Plan. Only the people in the area, familiar with its history and offerings, can make the Action Plan become reality.

As groups research and investigate the best way forward in each project area, the full financial implications will become known and applications for funding and fund-raising activities will take place.  It is recognised that Council and RDP will not have sufficient funds to carry out all the activities in this plan and other sources of funding will be required.  The full Village Plan provides details of potential opportunities to grasp.

The Steering Committee will liaise with Causeway Coast and Glens Borough Council on an ongoing basis to monitor progress and implementation of identified actions.

Appendix Socio Economic Analysis Macosquin

Usually resident population

On Census Day 27 March 2011, the usually resident population of Macosquin Settlement was 614 accounting for 0.03% of the NI total.

Households

On Census Day 27th March 2011, there were 614 people (100.00%) of the usually resident population) living in 247 households, giving an average household size of 2.49.

Demography

On Census Day 27th March 2011, in Macosquin Settlement:

- 21.82% were aged under 16 years and 13.68% were aged 65 years and over

- 48.53% of the usually resident population were male and 51.47% were female

- 38 years was the average (median) age of the population

Ethnicity, identity, language and religion

On Census Day 27th March 2011, in Macosquin Settlement, considering the resident population:

- 99.84% were from the white (including Irish traveller) ethnic group

- 4.07% belong to or were brought up in the Catholic religion and 91.86% belong to or were brought up in a ‘Protestant and Other Christian (including Christian related)’ religion

- 81.76% indicated that they had a British national identity, 4.07% had an Irish national identity and 26.06% had a Northern Irish national identity

*Respondents could indicate more than one national identity

On Census Day 27th March 2011, in Macosquin Settlement, considering the population aged 3 years old and over:

- 2.41% had some knowledge of Irish

- 16.32% had some knowledge of Ulster Scots

- 0.00% did not have English as their first language

Health

On Census Day 27th March 2011, in Macosquin Settlement:

- 18.08% of people had a long-term health problem or disability that limited their day-to-day activities

- 80.13% of people stated their general health was either good or very good

- 7.49% of people stated that they provided unpaid care to family, friends, neighbours or others

Housing and accommodation

On Census Day 27th March 2011, in Macosquin Settlement:

- 63.16% of households were owner occupied and 34.82% were rented

- 34.01% of households were owned outright

- 10.93% of households were comprised of a single person aged 65+ years

- 12.15% were lone parent households with dependent children

- 23.48% of households did not have access to a car or van

Qualifications

On Census Day 27th March 2011, considering the population aged 16 years old and over:

- 16.04% had a degree or higher qualification

- 57.08% had no or low (Level 1*) qualifications

*level 1 is 1-4 O Levels/GCE/GCSE (any grades) or equivalent

Labour market

On Census Day 27th March 2011, considering the population aged 16 to 74 years old:

- 62.56% were economically active, 37.44% were economically inactive

- 55.07% were in paid employment

- 3.96% were unemployed

Deprivation

The Northern Ireland Multiple Deprivation Measure (NIMDM) 2010 provides information on seven types of deprivation and overall measure of multiple deprivation for small areas. NISRA has recently been commissioned to initiate work to update this Measure with a view to publish results mid-2017. See the NISRA website for further information on Deprivation.

Wards are ordered from most deprived to least deprived on each type of deprivation and then assigned a rank. The most deprived is ranked 1, and as there are 582 wards, the least deprived ward has a rank of 582. The deprivation rankings for Mascoquin Ward are given in the table below.

|  | Rank Macosquin |
| --- | --- |
| Multiple Deprivation Measure | 355 |
| Income Deprivation | 313 |
| Employment Deprivation | 284 |
| Health Deprivation and Disability Deprivation | 426 |
| Education Skills and Training Disability | 399 |
| Proximity to Services Deprivation | 175 |
| Crime and Disorder | 411 |
| Living Environment | 279 |

A Better Future Together – A Community Plan for Causeway Coast and Glens 2017 - 2030

Northern Area Plan 2016 page 116